## Config
Ticket Name | Assignee | Milestone | Due Date | Labels
User Story>>Test>> UAA001 >> Login |  | Sprint 1 | 2024-06-28 | ["User_Story"]
Task >> Test>> Frontend >> Login | Bishesh Tuladhar | Sprint 1 | 2024-06-28 | ["CAT_REGULAR", "PLAT_FRONTEND"]
Task >> Test>> Backend >> Login | Suman Rimal | Sprint 1 | 2024-06-29 | ["CAT_REGULAR", "PLAT_BACKEND/CMS"]
Task >> Test>> API >> Login | Suman Rimal | Sprint 1 | 2024-06-30 | ["CAT_REGULAR", "PLAT_API"]
Task >> Test>> QA >> Login | Kabi Shakya | Sprint 1 | 2024-07-01 | ["CAT_REGULAR", "PLAT_QA"]